## Slide 1: Building the Right Support – Stakeholder Update Forum
We are currently letting people into the meeting from the lobby and will start shortly
21 February 2023

## Slide 2: Welcome and introduction
Welcome to the Stakeholder Update Forum meeting
To help the meeting run well:
        Please stay on mute unless you are talking to minimise background noise
        Please keep your video off unless you are talking

## Slide 3: Plan for the meeting
1. Welcome and introduction – 9.30am - 9.40am (10 minutes)
Building the Right Support Action Plan
2. Progress update on actions – 9.40am - 10.00am (20 minutes)
Wider Building the Right Support updates
3. Update from CQC – 10.00am - 10.20am (20 minutes)
4. Update from NHS England – 10.20am - 10.40am (20 minutes)
Discussion
5. Question and answer session – 10.40am - 10.55am (15 minutes)
6. Summary and close – 10.55am - 11.00am (5 minutes)

## Slide 4: Building the Right Support Action Plan
Tracy Raby, Building the Right Support Policy Lead

## Slide 5: Progress update on actions
In this update, we will look at:
Actions that have been completed since the publication of the Building the Right Support Action Plan in July 2022
Actions that have missed expected completion dates and the mitigation plans in place
Actions that are on track to be completed in the next quarter (April- June 2023)

## Slide 6: Actions completed since the publication of the Action Plan
Action | What we said we would do | Lead organisation
1b | Hold webinars with Principal Social Workers and sector partners to promote use of the Revisiting Safeguarding Practice guidance | DHSC
1d | Ensure that people with a learning disability and autistic people have received a safe and wellbeing review if they were in mental health inpatient care as at 31 October 2021 | NHS England
2a | Work on a refresh of the C(E)TR policy. The refreshed policy will have an increased focus on the physical health of people in hospital and include an increased emphasis on the importance of the actions that should follow from a C(E)TR | NHS England
2b | Issue Community Discharge Grant payment for the financial year 2022 to 2023 | DHSC
DRAFT – NOT FOR ONWARD CIRCULATION

## Slide 7: Actions completed since the publication of the Action Plan
Action | What we said we would do | Lead organisation
2e | Establish links between the Mental Health Casework Section (MHCS) and NHS England for future casework queries. Review cases highlighted by regional teams | Ministry of Justice
3g | Undertake peer reviews in an additional 4 Integrated Care Systems | NHS England
3j | Publish a range of guidance and information for commissioners to support them to commission for people’s lives and not just a service Hold webinars with sector partners to promote use of the guidance | Skills for Care Skills for Care
3n | Publish guidance in relation to minimum expectations for dynamic support registers | NHS England
DRAFT – NOT FOR ONWARD CIRCULATION

## Slide 8: Actions completed since the publication of the Action Plan
Action | What we said we would do | Lead organisation
4g | Fund a minimum of 5 local areas in the first year to trial different approaches to respite care/short breaks, targeting those children and young people who may need a different model of delivery from what is currently available in their area | DfE
4i | Update and publish the revised National Minimum Standards (NMS) for Residential Special Schools, reflecting responses to consultation | DfE
4j | Procure new Universal contract to provide continuing professional development (CPD) for education staff, including specific KPIs for support to autistic children and young people | DfE
5b | Undertake a rapid review of funding flows, which DHSC will make recommendations that DHSC will consider and act on as appropriate | DHSC
DRAFT – NOT FOR ONWARD CIRCULATION

## Slide 9: Actions that have missed expected completion dates
Action | What we said we would do | By when | Lead organisation | What we are doing now
1a | Complete review of inpatient advocacy and develop recommendations for next steps | Summer 2022 | NHS England | NHS England are continuing to work with partners to finalise the advocacy report
1e | Carry out Independent Care (Education) and Treatment Reviews (IC(E)TRs) for those in scope | End of 2022 | DHSC | DHSC, NHSE and CQC are working to complete IC(E)TRs by April 2023.
3e | Establish final report approvals for the What Good Looks Like report and develop a communications plan to make sure findings are communicated widely | September 2022 | LGA | Funding to finalise the What Good Looks Like report is awaiting final approval

## Slide 10: Actions that are due to complete between April-June 2023
Action | What we said we would do | By when | Lead organisation
1g | Expand programme of quality checked Positive Behavioural Support (PBS) training providers and develop PBS community of Practice | April 2023 | Skills for Care
1h | Implement a programme of personalised workforce development for the workforce that supports people with a learning disability and autistic people who may be at risk of admission or are ready to be discharged | April 2023 | Skills for Care
3h | Continue to roll out the accredited commissioning qualification to a cohort of current and aspiring commissioners | April 2023 | Skills for Care
3i | Roll out a training programme for senior leaders to increase their skills and knowledge to support local commissioners with 2 cohorts of senior leaders to have commissioning programme per annum | April 2023 | Skills for Care
5c | Review section 75 of the NHS Act 2006, post review, DHSC will published revised guidance on the use of pooled budgets | Spring 2023 | DHSC
DRAFT – NOT FOR ONWARD CIRCULATION

## Slide 11: CQC update

## Slide 12
CQC – our regulation of services for people with a learning disability and autistic people
February 2023
Debbie Ivanova Director for people with a learning disability and autistic people

## Slide 13
Azi is a 16 year old who has lived in a secure children’s home.
He requires intensive support to manage his distress and has a recent diagnosis of autism. His mother was unable to cope and felt he was a threat to her.
Commissioners approached a CQC home care provider and shared his care plan with them, advised that Azi was making good progress but had a court order in place, restricting his liberty.
They agree to support Azi and the local authority rented some accommodation for him.
The commissioned package of care did not meet CQCs definition of “personal care” and therefore CQC cannot regulate his care and support.

## Slide 14
What’s on our mind?
Children and adults don’t always have access to the right services, community support and places to call home.
Too many services are commissioned that don’t meet Right support, right care, right culture.
We need to reduce our reliance on hospital provision, getting it right for people where they live,
We need to focus on maintaining people’s health and wellbeing
We need less restrictive practice
We need to have regulation that safely covers those that need it, where they live

## Slide 15
Taking forward our regulatory approach
Our registration
We will continue to make sure that only services that meet Right support, right care, right culture are registered.
We will use conditions to stop people being placed in the wrong services.
Our inspection
We will continue to develop our approach to inspections. Focusing on observation, out of hours visits and looking to increase the number of times we cross the threshold. What is it really like to live in or use this service?
Our assessment
We will continue to look at how we can spots signs of closed culture early and support providers to get under the culture in their services.

## Slide 16
Shaping our new priorities
Health and well being
How can CQC, with its regulation of both health and care services play a part in improving health and well being?
Community support
How can CQC lever the development of high quality community support?
Reducing restrictive practice
How can CQC do more to reduce the use of restrictive practice?

## Slide 17: NHS England update

## Slide 18: Learning Disability and Autism Programme Dynamic Support Registers (DSRs) and Key Care (Education) and Treatment Reviews (C(E)TRs) Policy Changes.

## Slide 19: Policy Development
Co-production – we received over 300 responses from people with lived experience, professionals and stakeholders across the WHOLE system and both policy’s developed with Steering Groups with stakeholders and people with lived experience.
Consideration to wider system changes – New NHSE Operating Framework and other policy developments (Draft Mental Health Act Bill, BTRS Action Plan, SEND inspection Framework)
Learning from system reviews – LeDeR, Safe and Wellbeing Reviews and National Safeguarding Reviews

## Slide 20: Update on publication
The combined DSR CETR policy has now been published (25th January 2023).
C(E)TR guidance and DSR guidance are both included in the published policy.
There will be a three-month period between publication and implementation to allow time for the changes to be embedded. This is expected to be complete on 1st May 2023.

## Slide 21: Dynamic Support Registers
“A Dynamic Support Register (DSR) is the tool used in a local area to identify individual children, young people and adults with a learning disability, autism or both who are at risk or may become at risk of admission to a mental health inpatient setting without specific and timely Dynamic Support”
Note: the term “At Risk of Admission Register” was originally used, this term continues to be used in some areas. Similarly, the Dynamic Support Register is also known in some local areas as a Dynamic Support Database (DSD). The Draft Mental Health Bill (2022) uses the term “registers of people at risk of detention”.

## Slide 22: Making a DSR that is most useful to your area
DSR minimum requirements and standards
Working together to develop your local DSR
The best DSR for children, young people, adults & their families in your area

## Slide 23: DSR: Key consultation findings
There should be a standard approach to understanding people's needs and the support they might need.
People are not always clear on how to find their local Dynamic Support Register.
People are not always sure who is responsible for the Dynamic Support Register.
There should be no wrong door to ask for help!

## Slide 24: DSR: What we included in the policy...
Increased accountability for ICBs
Increased local visibility and understanding of the DSR
Increased focus on autistic people
Increased focus on identifying people at risk of admission to hospital

## Slide 25: DSR: What we included in the policy...
Greater focus on shared ownership across local systems to improve joint working.
Responsive to changing needs and risk
Dependant on co-produced local implementation
Greater focus on children and young people placed in 52-week residential schools and colleges

## Slide 26: DSR: Key changes to existing processes
A clear way to stratify the needs and risks of people
A Right to Self Refer onto the DSR
A clear ask to refer for keyworkers, C(E)TRs and support for unpaid carers
Includes people in inpatient mental health settings and links to commissioner oversight visits

## Slide 27: Care (Education) and Treatment Reviews
A C(E)TR is a meeting bringing together those responsible for commissioning and providing services (including nurses, social workers, local authority representatives, such as from housing and education, and health and social care commissioners) together with independent clinical opinion and those with lived experience of learning disabilities and/or autism, which includes people with a learning disability and/or autistic people and their family carers.
The aim of a C(E)TR is to check that a person who is either at risk of being admitted or who has already been admitted to a hospital setting is receiving appropriate care that meets their individual needs and that, where possible, challenges are overcome to support discharge to or continued care in the community.

## Slide 28: C(E)TR: Key consultation findings
Actions are often not followed up and no one is held accountable.
Physical health checks are often not happening or are not good enough.
Agendas can be too rigid and not created based on the person and their circumstances.
Advocates do not always attend and where they do their knowledge and relationship with the person is limited.

## Slide 29: C(E)TR: What we included in the policy...
Increased focus on advocacy
Increased focus on physical health
Increased focus on quality of life
Increased focus on accountability and quality assurance

## Slide 30: C(E)TR: What we included in the policy.....
Greater focus on all panel members having an equal voice.
Improved clarity on the escalation process.
Greater focus on matching of panel to the person.
Links to other processes (Care Programme Approach, Commissioner Oversight visits, Independent CETRs, keyworkers, Senior Intervenors).

## Slide 31: C(E)TR: Key changes to existing processes
Clearer on how to request a C(E)TR sooner than minimum timescales.
C(E)TRs to be undertaken for any person moving from one hospital to another.
C(E)TRs to be undertaken within 6 weeks of admission if community C(E)TR has taken place.
C(E)TR to be undertaken prior to any removal of a diagnosis of Learning Disability or Autism.

## Slide 32: CETR: Key changes continued
Payment structure for EbyEs and Clinical Experts
Mandatory Training for panel members
Option for same panel to undertake follow up review
Recommendation for a community follow up C(E)TR post discharge
New oversight process through Oversight Panels

## Slide 33: CETR and DSR policy next steps
Planned national information sharing events following publication.
Talking with partner organisations to support communication of the new policy.
Training being developed with Health Education England.
National research being commissioned into the effectiveness of C(E)TRs.
Refresh of the CETR Code of Practice, Toolkit and DSR Audit Tool to support the new policy.
CETR Key Lines Of Enquiry document being updated based on stakeholder feedback.
Regional exercise to baseline current compliance with ICBs

## Slide 34: Question and answer session

## Slide 35
Thank you for your time and participation
BtRS_Stakeholder_Update_Forum@dhsc.gov.uk